## Sheet1
Work Breakdown Structure
Project Plan
Activity | Duration
Phase 1 | 25 days
Database | 8 days
Development of employee and related tables (Team 1) | 4 days
Development of timecard and related tables (Team 1) | 4 days
Portal Design | 19 days
Design login and related screens (Forgot password, etc.) (Team 2) | 8 days
Design dashboard screen (Team 2) | 5 days
Design Schedule & Timecard (Team 2) | 6 days
Website functionality | 15 days
Login screen and related screen (Team 1) | 4 days
Dashboard (Team 1) | 5 days
Functionality Schedule and Timecard (Team 1) | 6 days
Bug testing | 7 days
Design & Functionality (Team 1 + 2) | 7 days
Phase 2 | 27 days
Time | 8 days
Design and functionality - Reporting (Team 1 + 2) | 8 days
Invoice | 13 days
Design and functionality - Mass approval and rejection (Team 1 + 2) | 6 days
Design and functionality - Handling sending back and forth TekSystems + MakarMotors (Team 1 + 2) | 7 days
Project | 8 days
Design and functionality - Starting/Ending/Creating projects (Team 1 + 2) | 4 days
Design and functionality - Members (Team 1 + 2) | 2 days
Design and functionality - Activites/Billable/Nonbillable (Team 1 + 2) | 2 days
Phase 3 | 13 days
Polishing (Team 1 + 2) | 6 days
Bug checking & fixing (Team 1 + 2) | 7 days
Total Days | 65 days